## Task_Table
Team | TOP KEK |  | Semseter 1 times |  | Semseter 1 times
team id | 3 |  | start date | end date | start date | end date
Origonal Document writter | cormac |  | 2014-10-06 | 2014-12-26 | 2015-01-12 | 2015-02-16
|  |  | Number of weeks |  | Number of weeks |  | Total weeks
|  |  | 11 |  | 5 |  | 16
|  |  | Alotted hours |  | Alotted hours |  | Total hours
|  |  | 40 |  | 40 |  | 80
|  |  | Average per week |  | Average per week |  | Average
|  |  | 3 |  | 8 |  | 11
Member | Time Spent | Hours left | card
Abdullah Alkhashty | 5 | 75
Au, Yee Tim | 17 | 63
Calvin Chan | 8.25 | 71.75
Cormac Brady | 44.75 | 35.25
Henry Hollingsworth | 26 | 54
Rhys Howard | 10 | 70
James Portch | 6.5 | 73.5
Karl Franks | 14.5 | 65.5
Kieran Lynch | 3 | 77
Melissa Smith | 11 | 69
Scott Lockett | 7.3 | 72.7
Zach Yewman | 22 | 58

## Cormac Brady
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Cormac Brady
administer group tasks | 1 | 1 | crate final draft | 1 | 2
keep project plans updated | 0.5 | 0.5 | review project plan | 8h | 1.5 | Recurring tasks total | 20.75 | Individual tasks total | 1.5
|  |  | create timsheet | 1 | 2 |  |  | Including all weeks | 24
|  |  | monitor and review git submissions | 1 | 4
|  |  | create gant chart | 1 | 1 | Grand Total | 44.75
|  |  | database design | 1 | 0.25
|  |  | database implementation | 1 | 2
|  |  | document review meetings | 1 | 1
|  |  | web php | 1 | 7

## Abdullah Alkhashty
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Abdullah Alkhashty
|  |  | project plan proof reading | 0.3 | 1
|  |  | writing html | 2 | 2 | Recurring tasks total | 5 | Individual tasks total | 0
|  |  | data addition | 1 | 2 |  |  | Including all weeks | 0
[6 empty] | Grand Total | 5

## Au, Yee Tim
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Au, Yee Tim
|  |  | project plan use-case diagrams | 1 | 2
|  |  | project plan finalisation | 1 | 3 | Recurring tasks total | 17 | Individual tasks total | 0
|  |  | Training Abdullah - EXTRA WORK | 0 | 3 |  |  | Including all weeks | 0
|  |  | gihub QA - EXTRA WORK | 0 | 3
|  |  | requirements progress | 1 | 6 | Grand Total | 17

## Calvin Chan
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Calvin Chan
|  |  | project plan introduction | 0.5 | 2
|  |  | reviewing documents | 2 | 3 | Recurring tasks total | 8.25 | Individual tasks total | 0
|  |  | review test spec | 2 | 2 |  |  | Including all weeks | 0
|  |  | icon | 1 | 1.25
[6 empty] | Grand Total | 8.25

## Henry Hollingsworth
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Henry Hollingsworth
|  |  | project plan User interface | 1 | 2
|  |  | Testing document android | 1 | 1 | Recurring tasks total | 26 | Individual tasks total | 0
|  |  | Android app development | 10 | 9 |  |  | Including all weeks | 0
|  |  | document review meetings | 3 | 2
|  |  | java | 2 | 12 | Grand Total | 26

## Rhys Howard
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Rhys Howard
moniter and revew git submishions | 1 | 0.5 | document review meetings | 3 | 2
[6 empty] | Recurring tasks total | 2 | Individual tasks total | 0.5
[8 empty] | Including all weeks | 8
[6 empty] | Grand Total | 10

## James Portch
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | James Portch
|  |  | document review meetings | 2 | 1
|  |  | spell cheacking desin documet | 0.5 | 0.5 | Recurring tasks total | 6.5 | Individual tasks total | 0
|  |  | alterling documents | 1 | 3 |  |  | Including all weeks | 0
|  |  | data addition | 1 | 2
[6 empty] | Grand Total | 6.5

## Karl Franks
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Karl Franks
|  |  | project plan overview | 1 | 3
|  |  | server/database test document | 3 | 2 | Recurring tasks total | 14.5 | Individual tasks total | 0
|  |  | php inteface creation | 0.1 | 0.5 |  |  | Including all weeks | 0
|  |  | project plan web UI | 1 | 1
|  |  | php edit/delete buttons | 1 | 1 | Grand Total | 14.5
|  |  | php | 7 | 7

## Kieran Lynch
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Kieran Lynch
|  |  | web application test doc | 1 | 1
|  |  | web app html/css/github hosting | 2 | 2 | Recurring tasks total | 3 | Individual tasks total | 0
[8 empty] | Including all weeks | 0
[6 empty] | Grand Total | 3

## Melissa Smith
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Melissa Smith
admin group | 0.5 | 0.25 | project plan (risk analysis) | 1 | 1
|  |  | desin (doc intoducton) | 1 | 1 | Recurring tasks total | 7 | Individual tasks total | 0.25
|  |  | document review meetings | 2 | 1 |  |  | Including all weeks | 4
|  |  | document editing | 1 | 4
[6 empty] | Grand Total | 11

## Scott Lockett
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Scott Lockett
|  |  | risk analysis | 1 | 1
|  |  | website desin | 2 | 5 | Recurring tasks total | 7.3 | Individual tasks total | 0
|  |  | server php query methods | 1 | 1.3 |  |  | Including all weeks | 0
[6 empty] | Grand Total | 7.3

## Zach Yewman
Recurring tasks | Estimated time | Actual Time | Individual tasks | Estimated time2 | Actual Time2 | name | Zach Yewman
|  |  | project plan android ui | 2 | 4
|  |  | android record transmission | 10 | 5 | Recurring tasks total | 22 | Individual tasks total | 0
|  |  | web php | 2 | 13 |  |  | Including all weeks | 0
[6 empty] | Grand Total | 22